## Sulpher Site
Application Name:- Timesheet application
Version Number - V 3.0.0.0 |  |  |  |  | Priority/ Severity level :- |  | Bug status:- | https://ignatiuzsoftware-2560be1aea5061.sharepoint.com/AutomationSite/Timesheet_V_2.6.1.7/Office365Timesheet/ | 9gMpkpop2QWJdcQa3KsZ
Date:-28-5-2019 | [6 empty] | Passed | https://ignatiuzsoftware-2560be1aea5060.sharepoint.com/AutomationSite/Office365Timesheet/ | oSGoisaM8ZmGsALcE0dh
Author-Priyanka Saroch |  |  |  |  | High |  | Failed
[5 empty] | Medium |  | Reopen/ Pending
[5 empty] | Low |  | Open
New
Sr No. | Bug Id | Module Name | Description | Priority | Severity | Browser / Image links | Bug Status | QA comments | Dev Status | Release Information
| TM_1 | Advance Report | Month year and one week date is selected data is Not getting searched | High | High | Scrennshot | Passed 13-06-2019 | Client Reported issue | Fixed 13/06/2019
| TM_2 | Advance Report | When we select Year and Month is left blank then No data is getting searched | High | High | Scrennshot | Passed 13-06-2019 |  | Fixed 13/06/2019
| TM_3 | Advance Report | On changing setting as DD/MM/YYYY date format is coming wrong at timesheet data table even when we are selecting date range it is coming wrong | High | High | Scrennshot | Passed 19/06/2019 |  | Fixed 14/06/2019
| TM_4 | Advance Report | All the months ,year and 1-week range is selected data is not getting searched | High | Medium | Scrennshot | Passed 13-06-2019 | Client Reported issue | Fixed 13/06/2019
| TM_5 | Advance Report | When searched for full month is should not show data of next month Timesheet data is displayed wrong | Medium | Medium | Scrennshot | Passed 13-06-2019 | Client Reported issue | Fixed 13/06/2019
| TM_6 | Advance Report | When created timesheet of year ending week and searched for the timesheet Next year timesheet should not get searched | Medium | Medium | Scrennshot | Passed 13-06-2019 |  | Fixed 13/06/2019
| TM_7 | Advance Report | Unable to convert timesheet data in chart form when Date Range is selected | Medium | Medium | Scrennshot | Passed 13-06-2019 |  | Fixed 13/06/2019
| TM_9 | Advance Report | When we search timesheet data by selecting Dates from One month Starting week ending date to next month Week starting date It is not getting searched even when Year is filled | Medium | Medium | Scrennshot | Passed 13-06-2019 |  | Not an issue
| TM_10 | Advance Report | When Month and Year are left Blank and Only From and To dates are selected then Unable to search for Timesheet data Notice: I have selected dates of Year 2023 and 2024 | Medium | Medium | Scrennshot | Passed 19-06-2019 |  | Not reproducable at developer end
| TM_11 | Advance Report | Billable hours are coming Zero when I have created timesheet of Year 2020 | Medium | Medium | Scrennshot | Passed 13-06-2019 |  | Not an issue
| TM_12 | Export Data | When exported excel sheet Duplicate entries are coming here.Please fix it for word format also. | Medium | Medium | Screenshot | Passed 19-06-2019 |  | Fixed 19-06-2019
| TM_13 | User's Page | Steps: 1.I have added Employee with this manager 2.I clicked on edit button and updated the Manager with already existing manager 3.It should not take duplicate entries of employee with same manager.Please fix it. Notice: At first time when we add employee with same manager it gives proper validation but when we edit the same it takes duplicate entries | High | Medium | Scrennshot | Reopen/ Pending 27/06/2019
| TM_14 | Settings | IN DOR date format is coming wrong in calender boxes Please fix it for Weekly Overtime Report also Here Date format I have set is DD/MM/YYYY | High | Medium | Scrennshot | Reopen/ Pending 27/06/2019
| TM_15 | Timesheet | I have deleted all timesheet from employee portal then why OT,AH and RH are displaying here it should be zero | High | High | Scrennshot | New 27-06-2019 | It was working in Previous Release
Scrennshot
Scrennshot
Scrennshot
Scrennshot
Scrennshot
Scrennshot
Scrennshot
Scrennshot
Scrennshot
Scrennshot
Scrennshot
Scrennshot

## Paid Version
Application Name:- Timesheet application
Version Number - V 3.0.0.0 |  |  |  |  | Priority/ Severity level :- |  | Bug status:- | https://ignatiuzsoftware-2560be1aea5061.sharepoint.com/AutomationSite/Timesheet_V_2.6.1.7/Office365Timesheet/ | 9gMpkpop2QWJdcQa3KsZ
Date:-28-5-2019 | [6 empty] | Passed | https://ignatiuzsoftware-2560be1aea5060.sharepoint.com/AutomationSite/Office365Timesheet/ | oSGoisaM8ZmGsALcE0dh
Author-Prachi Tanwar |  |  |  |  | High |  | Failed
[5 empty] | Medium |  | Reopen/ Pending
[5 empty] | Low |  | Open
New
Sr No. | Bug Id | Module Name | Description | Priority | Severity | Browser / Image links | Bug Status | QA comments | Dev Status | Release Information
1 | TM_01 | Project and Task Settings | Unable to make Project Active after making it Inactive.Please fix it. | High | Medium | Screenshot | Passed 19/06/2019 |  | Fixed 13/06/2019
2 | TM_02 | Assign Project to task | When Logged in as manager Unable to navigate at Assign Project to Task Page. IE(Issue) | Medium | Medium | Screenshot | Passed 19/06/2019 |  | Fixed 13/06/2019
3 | TM_03 | Advance Report | Validation message should come when "From date should be less then to date". Date format is DD/MM/YYYY | High | Medium | Screenshot | Passed 19/06/2019 |  | Fixed 13/06/2019
4 | TM_04 | Advance Report Automation | Year Selection Dropdown should Close when we are selecting Date From To Date Calender | Low | Low | Screenshot | New 19/07/2019 | This issue was coming during Automation | I am not getting this issue when i select year dropdown and calender manually
5 | TM_05 | Report(Free Version) | When we select any Project from filters then Why tasks are coming Multiple times.Please fix it. | Medium | Medium | Screenshot | Passed 26/06/2019 |  | Fixed 25/07/2019
6 | TM_06 | UI Issue | While importing Projects the Footer should be of same color Please get it fixed for task also | Medium | Medium | Screenshot | Passed 26/06/2019 |  | Fixed 25/07/2019
7 | TM_07 | Project and Task Setting By Automation and Manual | Unable to Import Projects | High | High | Screenshot | Passed 26/06/2019 |  | Not getting
8 | TM_08 | Importing Task | After importing task duplicate tasks are getting Imported Please fix it. | High | High | Screenshot | Passed 26/06/2019 |  | Not getting
9 | TM_09 | Assign Project to task | While assigning Project to Task Headers and Footers are getting Disturbed | Medium | Medium | Screenshot | Passed 26/06/2019 |  | Fixed 25/07/2019
10 | TM_10

## SIWI
Application Name:- Timesheet application
Version Number - V 3.0.0.0 |  |  |  |  | Priority/ Severity level :- |  | Bug status:- | https://ignatiuzsoftware-2560be1aea5061.sharepoint.com/AutomationSite/Timesheet_V_2.6.1.7/Office365Timesheet/ | 9gMpkpop2QWJdcQa3KsZ
Date:-28-5-2019 | [6 empty] | Passed | https://ignatiuzsoftware-2560be1aea5060.sharepoint.com/AutomationSite/Office365Timesheet/ | oSGoisaM8ZmGsALcE0dh
Author-Priyanka Saroch |  |  |  |  | High |  | Failed
[5 empty] | Medium |  | Reopen/ Pending
[5 empty] | Low |  | Open
New
Sr No. | Bug Id | Module Name | Description | Priority | Severity | Browser / Image links | Bug Status | QA comments | Dev Status | Release Information
1 | SIWI_01 | Detailed Report | Using filter : When Searching for 1 week timesheet data wrong data is coming It should display searched data only It is not working using Project and work order flter Date format is DD/MM/YYY | High | Medium | Screenshot | Passed 26-06-2019
2 | SIWI_02 | Setting | Validation should come here "To date should always be greater than from date" Please get it fixed for both date format DD/MM/YYYY and MM/DD/YYYY | High | Medium | Screenshot | Passed 26-06-2019
3 | SIWI_03 | New Timesheet | Please import a loader after clicking on Submit or draft button Please fix it for Manager Portal also | Low | Low | Screenshot | Reopen/ Pending 26-06-2019
4 | SIWI_04 | All Pages | The file name should be same as "Page name" In this case it is: Detail Report Please fix it for Account Report Also | Low | Low | Screenshot | Passed 26-06-2019
5 | SIWI_05 | Project and Work order Settings | I clicked on edit button and unchecked the "Work hour" Checkbox and getting validation here It should get update when we want to change the Work hours settings | High | Medium | Screenshot | Reopen/ Pending 26-06-2019 | Steps: 1.First add Work order 2.After adding uncheck the work hour checkbox
6 | SIWI_06 | Detail Report | When i am selecting manager whose timesheet is not created Message should display "No Record Found" Please fix it for Chart form also | Medium | Medium | Screenshot | New 01/07/2019
7 | SIWI_07 | Detail Report | Date format i have set here is DD/MM/YYY it is coming correct in Timesheet Data table | High | Medium | Screenshot | New 01/07/2019
8 | SIWI_08

## New Changes Koops
[5 empty] | Priority/ Severity level :- |  | Bug status:-
Passed
[5 empty] | High |  | Failed
[5 empty] | Medium |  | Reopen/ Pending
[5 empty] | Low |  | Open
New
Sr No. | Bug Id | Module Name | Description | Priority | Severity | Browser / Image links | Bug Status | QA comments | Dev Status | Release Information | Bug Reported By QA
1 | Koops_01 | State | Unable to delete the state .Please fix it. | Medium | Medium | Screenshot | Passed 27-06-2019 |  | Fixed 19-06-2019
2 | Koops_02 | Viewing Timesheet | Unable to view Timesheet data at Employee portal as well as manager portal As well as date fields are also coming blank in manager Portal Notice: Issue occur only when date format is set as DD/MM/YYYY | High | High | Screenshot | Passed 27-06-2019 | Please fix it for manager and Employee Portal | Fixed 19-06-2019
3 | Koops_03 | New Timesheet | I have inserted here numberwithoutt selecting project Number a validation message should appear "Project Number is Required" | Low | Low | Screenshot | Passed 01-07-2019 |  | Fixed 27-06-2019
| Koops_04 | New Timesheet | Loader should not come when validation appear | Medium | Medium | Screenshot | Passed 01-07-2019
| Koops_05 | New Timesheet | I have already created timesheet of this date then on creating new timesheet same date is coming | High | Medium | Screenshot | Passed 01-07-2019
| Koops_06 | New Timesheet | It should give validation "Project number " is required Note: It only happens on adding row | Medium | Medium | Screenshot | Passed 01-07-2019
| Koops_07 | New Timesheet | Loader is running indefinitely when we enter value for Auto save Draft timesheet | High | High | Screenshot | Passed 01-07-2019
| Koops_08 | New Timesheet | When firstly i created timesheet so Week ending date was coming "July" and when i Want to create second timesheet it is coming correct .When third time you will create it weak ending day will come as it was first timesheet. It should not allow to create duplicate timesheets | Medium | Medium | Screenshot | New 01-07-2019 | Steps: 1.Create timesheet of one week 2.Again create timesheet (Week ending days will come different) 3.Whne third time you will create it weak ending day will come as it was first timesheet
| Koops_09 | New Timesheet | User should not be able to create duplicate date timesheets. The Week ending date textbox should be disable on Updating the viewed timesheet | High | High | Screenshot | Passed 24-07-2019 |  | Fixed (23-07-2019)
| Koops_10 | New Timesheet | On Clicking on New Timesheet and updating the duplicate weekending date the validation should get fired | High | High | Screenshot | Passed 24-07-2019 |  | Fixed (23-07-2019)
| Koops_11 | New Timesheet | Why i am Unable to delete second row from Timesheet ? | Medium | Medium | Screenshot | Passed 24-07-2019 |  | Fixed (23-07-2019)
| Koops_12 | Employee Portal | Employee Portal: On clicking on Project tab Radio button options should be "Project" and Import Project | Medium | Medium | Screenshot | Passed 24-07-2019 |  | Fixed (24-07-2019)
| Koops_13 | Manager Portal | Manager Portal :When we open Manager Portal in New Link then view timesheet on same tab then Timesheet data is not coming | High | Medium | Screenshot | Passed 29-07-2019 | This issue is only coming on Manager Portal | Fixed (25-07-2019)
| Koops_14 | Timesheet | On viewing the timesheet this validation message should not come | High | Medium | Screenshot | New 24-07-2019
| Koops_15 | Auto save draft Timesheet | The Loader continously runs after adding Numbers in rows for saving timesheet as Draft When Date format is DD/MM/YYYY | Medium | Medium | Screenshot | Passed 29-07-2019
| Koops_16 | New Timesheet Deleting rows | Deleted row (ie. 8th Row ) and Same Project Name 6th row gets deleted | Medium | Medium | Screenshot | Passed 02-08-2019
| Koops_17 | New Timesheet | Create new timesheet and View that timesheet Add row into it and add number for saving timesheet as draft . Loader runs continoulsy and getting this error.please fix it. | Medium | Medium | Screenshot | Passed 02-08-2019 | It was working in Previous Release
| Koops_18 | New Timehsheet | If we have submitted the timesheet with blank week number row in it then on viewing the timesheet blank row should not come.But Project numbers are selected | High | Medium | Screenshot | Passed 02-08-2019
Koops_19

## Bulk Data
Projects | Project task | Description | Projects | Project task | Description | Projects | Project Task
[6 empty] | GSA/PRJ/17/126 - UniTech | Design Meeting
Consulting - myTimeTrack at -Timesheet add-in | Design Meeting |  | GSA/PRJ/17/126 - UniTech | Design Meeting | Review meeting with manager for code and updates of site | GSA/PRJ/17/126 - UniTech | Design Review
| Design Review |  |  | Design Review |  | GSA/PRJ/17/126 - UniTech | Development task
| Development task |  |  | Development task | 1. Generate the form code. 2. Create script for loading 3. Test the coe in debugging mode 4. Fix the QA issues 5. Write code for submission of data | GSA/PRJ/17/126 - UniTech | Site - Commissioning
| Testing app |  |  | Site - Commissioning |  | GSA/PRJ/17/126 - UniTech | Design- Auto CAD
| c | User Roles |  | Design- Auto CAD
| Task insertion in daily sheets | Users |  | Material - FollowUp |  | Consulting - myTimeTrack | 56 -Material - FollowUp
| Task review | Projects |  |  |  | Consulting - myTimeTrack | 789 :- Engineering - Meeting
| Task Approval | Project Tasks |  |  |  | Consulting - myTimeTrack | 35: Design- Material Specification
| Track Time | Reports |  |  |  | Consulting - myTimeTrack | 12 Site -Installation
| Report extraction | License | TM-Dev |  |  | Consulting - myTimeTrack | 1st Track Time
|  | Help | TM-Design | Engineering - Meeting |  | Consulting - myTimeTrack | 890 :- Report extraction
2017 APP Review - Testing myShowcase App |  |  | TM-Install | Design- Material Specification | Assign Project and task | Consulting - myTimeTrack | Touch Table - Object detection
2017 IL QIP Audit - HR Compliance | Hiring tasks | 1. Short list the resume 2. Interview for first round 3. Shortlist the candidates 4. finalize the candidates | TM-Test | Site -Installation |  | Consulting - myTimeTrack | Miscellaneous Works
| Shortlisting CV of candidates |  | TM- BOM
Consulting - SDLC Review - Multiple Projects - TPP/P3 |  |  | TM- RND | Design BOM |  | Consulting - myTimeTrack at -Timesheet add-in4 | Make Coaster for Object detection
Corrosion Control - of all the working site's of the Company | Performance review of the site | 1.Generate high traffic onsite 2. Generate excess load 3. Used JMeter scripts for load creation |  | Implement Google Analytics code on click of download. | 1. Get started with Analytics 2. Analytics Help 3. R& D on increasing the analytical code 4. report generation of the organizational site. | Consulting - myTimeTrack at -Timesheet add-in4 | TIFF Intranet - Graph API issue fixes for Schedule and Tasks.
Consulting - Process Technical Assistance - Scoutfoto | Event creation |  | HM-Dev | R&D to install sharepoint add-ins in on premises | 1.R & D on Status Report on Assignment 2.Support Vector Machine 3. Difference Between Regression and Classification | Consulting - myTimeTrack at -Timesheet add-in4 | Scrum call
| Image tagging |  | HM--Design | Deploy updated code on staging |  | Consulting - myTimeTrack at -Timesheet add-in4 | Testcases verification of trainees
| Image processing |  | HM--Install |  |  | Consulting - myTimeTrack at -Timesheet add-in4 | Meeting - With Deepesh & Ashwin about Photo Booth app
| Image download |  | HM--Test |  | 1. Fixes the assign issues 2. Review the developed code 3. Testing the fixed issues in debugging mode | Consulting - SDLC Review - Multiple Projects - TPP/P | TIFF site - final design of html page
| Site design updates |  | HM-- BOM |  | 1. Generate IP address 2. Contact to administrator 3. Set the permissions on the site 4. Review the generated address | Consulting - SDLC Review - Multiple Projects - TPP/P | R&D on how can we get data from list in spfx web part
| Review meeting |  | TM- RND |  | 1. write code for orientation2. check the code in debugging mode. 3. test the fixes 4. Meeting with the team for code review 5. Testing in various browsers
| KT of Scoutfoto to Prakhar | Give KT for site working and Credentials access |  |  | Review meeting with manager for code and updates of site | Design Meeting | Design Scrum call
| Get user IP address and add in database when user click on download button. | 1. Generate IP address 2. Contact to administrator 3. Set the permissions on the site 4. Review the generated address |  |  | Create video for site implementation | Design Meeting | Create Login As Permission and LoginActivity lists on Maplewood
| Check issue send By Rajesh - IPTC Writer is taking high CPU usage. | 1. Test the fixes of the site 2. Did regression testing 3.View design issues |  |  | Give KT for site working and Credentials access | Design Meeting | Design- Material Specification
| Correct profile picture orientation | 1. write code for orientation 2. check the code in debugging mode. 3. test the fixes 4. Meeting with the team for code review 5. Testing in various browsers |  |  | 1. Test the fixes of the site 2. Did regression testing 3.View design issues
[6 empty] | Design Review | Verify DRNF and NHC Forms on MapleWood
|  |  | GAS/PRJ/17/160- SACYR UCSF | Design Meeting |  | Design Review | Testcases verification of trainees
|  |  |  | Design Review |  | Design Review | Miscellaneous Works
Development task
|  |  |  | Site - Commissioning |  | GSA/PRJ/17/126 - UniTech | Design Meeting
|  |  |  | Design- Auto CAD |  | GSA/PRJ/17/126 - UniTech | Design Review
|  |  |  | Material - FollowUp |  | GSA/PRJ/17/126 - UniTech | Development task
GAS/SER/17/094 - Veolia | Design Meeting | Review meeting with manager for code and updates of site |  | Engineering - Meeting |  | GSA/PRJ/17/126 - UniTech | Site - Commissioning
| Design Review |  |  | Design- Material Specification |  | GSA/PRJ/17/126 - UniTech | Design- Auto CAD
| Development task | 1. Upload the site for deployment 2. Review the code |  |  |  | GSA/PRJ/17/126 - UniTech | QA scrum call
| Site - Commissioning |  |  |  |  | GSA/PRJ/17/126 - UniTech | KT of moodle from Priyanka
| Design- Auto CAD |  | Richa | 30/40 |  | GSA/PRJ/17/126 - UniTech | Change request of myShowcase app - 10-08-2018
| Material - FollowUp |  | Priya | 30/40 |  | GSA/PRJ/17/126 - UniTech | Check issue send By Rajesh - IPTC Writer is taking high CPU usage.
| Engineering - Meeting |  | Pratibha | 37/40
| Design- Material Specification |  | harshit | 34/40 | 6zGCMkz6ayZEhKkQgMPE | Hazlet VMS | Code Review for Functionality Development and Data Base Analysis
|  |  | shadab |  |  | Hazlet VMS | Testing of Hazlet
|  |  | vineeta | 31/40 |  | Hazlet VMS | Correct profile picture orientation
|  |  | ankit | 31/40
|  |  | Pragya | 29/40 |  | HelpDesk | Updating user manual of helpdesk
[6 empty] | HelpDesk | Issue fixes
Myhub | Task review |  |  |  |  | HelpDesk | Testcases verification of trainees
[6 empty] | HelpDesk | Creating user manual document of helpdesk
| Task Approval |  |  |  |  | HelpDesk | Help desk document Review (Prakhar)
Track Time
| Report extraction |  |  |  |  | HOA Mobile App Stage | Testcases verification of trainees
|  |  | TM Dev |  |  | HOA Mobile App Stage | Miscellaneous Works
GSA/PRJ/056 - Metito Over | Design Meeting |  | TM Design |  |  | HOA Mobile App Stage | Understanding the Byer's App
| Design Review |  | TM Install
| Development task |  | TM Test |  |  | HOA Stage | Mobile Automation.
| Site - Commissioning |  | TM BOM |  |  | HOA Stage | Review about author (Priyanka G) 12_12_2017
| Design- Auto CAD |  | TM RND |  |  | HOA Stage | Design- Material Specification
Material - FollowUp
| Engineering - Meeting |  | HM Dev |  |  | Timesheet | Timesheet Sheet knowledge base
| Design- Material Specification |  | HM Design |  |  | Timesheet | Testing of timesheet app - V.5.0(Fixes)
| Site -Installation |  | HM Install |  |  | Timesheet | Replicate the timesheet issues. (Client reported issues)
| Design BOM |  | HM Test
HM BOM
TM RND
Consulting - Culture Action Group
Consulting - myTime
Consulting - Process Technical Assistance
Emerging Contaminant Readiness
Environmental Compliance - Waste Disposal
HOS Contractor Management
Acquisition Process Effectiveness
Capital Contract Management

## 2.1.6.10 + ankoop
Application Name:- Timesheet application
Version Number - V 2.1.6.10 |  |  |  |  | Priority/ Severity level :- |  | Bug status:-
Date:-25-3-2019 |  |  |  |  | Critical |  | Passed
Author-Priyanka Saroch |  |  |  |  | High |  | Failed
[5 empty] | Medium |  | Reopen/ Pending
[5 empty] | Low |  | Open
New
Sr No. | Bug Id | Module Name | Description | Priority | Severity | Browser / Image links | Bug Status | QA comments | Dev Status | Release Information
1 | TM_N_01 |  | When a user is already a manager and a employee of old time sheet then in this case the super manager feature should show some pup-up that cannot be madde super manager //// or //// remove it from employee role and all the tmeshet of the employe role should be approved first and then should be make a Super manager |  |  | Screenshot | Passed - 29-3-2019 |  | Fixed(28-03-2019).
2 | TM_N_02 |  | on UserRole page "Super manager" heading id not coming | Critical |  | Screenshot | Passed - 27-3-2019 |  | Fixed
3 | TM_N_03 |  | Userole association are again not working properly | High |  | Screenshot | Passed - 28-3-2019 | It is hapening with manager email id | Fixed(27-03-2019)
4 | TM_N_04 |  | In Grant permission page on App User dropdown should be shown in alphabetical order |  |  | Screenshot | New - 25-3-2019
5 | TM_N_05 | Advanced report - IGNA paid version | Super manager, Mnager,Employee, Project, Project task drop dowm should be arranged alphabetically |  |  | Screenshot | Passed - 29-3-2019 |  | Fixed(29-03-2019)
6 | TM_N_06 |  | Also make the navigation links in single link on different pages it's behaving in two links this should not happen | Low | Low | Screenshot | Reopen/ Pending - 29-3-2019 | IN emplloyeee account on project page its not coming correct | Fixed(29-03-2019)
7 | TM_N_07 |  | Upload doucmnet page navigation link and page name should be same, in employe manager as it cannot upload so can make it documnet librady but in admin keep it upload documnet on both place navigation page heading |  |  | Screenshot | Passed - 29-3-2019 | In admin its upload document and in other account its document library | Fixed(29-03-2019)
8 | TM_N_08 |  | When the color is changed from blue to anyother, On Project and task setting page login as dropdown is been misplaced from its position | High |  | Screenshot | Passed - 29-3-2019 | Due to fixing of this the space between logo and navigation links is beem disturbed on various pages as timeshet settings page | Fixed(28-03-2019) Fixed(29-03-2019)
9 | TM_N_09 |  | Here in the note the bench mark space between the 2 words should be removed After full stop space of one letter should be added | Medium |  | Screenshot | Passed - 28-3-2019 |  | Fixed(28-03-2019)
10 | TM_N_10 |  | When the name or user is changed from Name + surname to surname + name then in approved reports of employs and manager the timesheet value is comiing 00 ---- seeger | High |  |  | Block- 29-3-2019 |  | Not an issue.
11 | TM_N_11 |  | When color is changed the selected font also get changed this should not happen | Medium |  |  | New - 26-3-2019
12 | TM_N_12 |  | Not able to save any value on bench mark settings page | Critical |  | Screenshot | Passed - 29-3-2019 |  | Fixed(29-03-2019)
13 | TM_N_13 |  | On Assign Project & Task page when we select Project the below gid gets colapsed , socan we just stop the collision OR can show the previous values of selected projects |  |  |  | Passed - 29-3-2019 | Here in project task its not fixed its only fixed in project dropdwon | Fixed(29-03-2019)
14 | TM_N_14 |  | On session expire if timeshet is tried to be submitted then its not submited and error is coming in console |  |  | Screenshot | New - 27-3-2019 |  | Fixed(09-04-2019)
15 | TM_N_15 | User / userrole page | When on click here excel format is downloaded then it should get downloaded with the same name of the imporet page as on Employe manager page its getting downloded with project excel name | High |  | Screenshoot | Passed - 29-3-2019 |  | Format link is not ready for employee and manager. Fixed(29-03-2019)
16 | TM_N_16 |  | The downloaded excel is of project import formate | Critical |  | Screenshot | Passed - 29-3-2019 |  | Format link is not ready for employee and manager. Fixed(29-03-2019)
17 | TM_N_17 |  | On User page the excel which is uploaded is saying that the excel format is incorrect | Critical |  |  | Passed - 28-3-2019 |  | Fixed(27-03-2019)
18 | TM_N_18 |  | Heading on Non-existing user should be role ID | Medium |  | Screenshot | Passed - 28-3-2019 |  | Fixed(28-03-2019)
19 | TM_N_19 |  | The timesheet s should be small always the sentence should be "If you want these users to be added in Timesheet, then you must add them in site user list. " | Low | High | Screenshot | Passed - 28-3-2019 |  | Fixed(27-03-2019)
20 | TM_N_20 |  | If project is inactive and its associated task is ben created then they also come inactie that ok but on the same page same time without refreshing the page if the project is made active then the assign task remains inactive. | High |  |  | Passed - 29-3-2019 |  | Fixed(29-03-2019)
21 | TM_N_21 |  | Weekendingday issue - client issues | Critical |  |  | Passed - 28-3-2019 |  | Fixed(27-03-2019)
22 | TM_N_22 |  | When the license is just updated and user directly goes and click on " Click here to see non-existing user's" link then for the first time its doesnot show any data . As i have imported managers in the page and again clicks the same link the data starts appearly . This should not happen. | High |  | Screenshoot | Block- 29-3-2019 |  | Data will be display after import excel. If non-existing user is present in the excel sheet.
23 | TM_N_23 |  | No logs are getting generated also the previous logs are not getting shown Do remember to add logs on Timesheet setting page | Critical | High | Screenshort | Passed - 29-3-2019 |  | Fixed (29-03-2019).
24 | TM_N_24 |  | The sorting should be either by date or day as here its not coming proper even if its date |  |  | Screenshort | Passed - 28-3-2019 |  | Fixed(28-03-2019).
25 | TM_N_25 |  | In both employee and manager account daily report link is getting visible |  |  | Screenshort | Passed - 28-3-2019 |  | Fixed(28-03-2019).
26 | TM_N_26 |  | 1. on click on the daily link also the value in the grid is conimg 2. Withour selection if searched is cliecked then also value is geting searched 3. When billable is hidden then also here on daily report page the two colmum are getting visible 4. This should be only Manager as not center is there |  |  | Screenshort | Passed - 28-3-2019 |  | - According to the requirement data should be display on page load. - No validation is required for dropdown selection. 3. Fixed(28-03-2019). 4. Fixed (28-03-2019).
27 | TM_N_27 |  | On daily report page when no record found message come a fullstop should be added. Also the 2nd two letters should be in samll case only first letter should start with capital letter. |  |  | Screenshort | Passed - 28-3-2019 |  | Fixed (28-03-2019).
28 | TM_N_28 |  | As no validation is required on seeger daily report page so please removed * mark from manager dropdown |  |  | Screenshort | Passed - 28-3-2019 |  | Fixed (28-03-2019).
29 | TM_N_29 |  | This sheet was created by 3 benchmark as now i have changed benchmark to 8 and as i m editing its not getting edited that is OK as the benchmark was 3 but validation is coming wrong |  |  | Screenshort | Passed - 29-3-2019 |  | Fixed (29-03-2019).
30 | TM_N_30 | benchmark domain check | in admin section super manager dropdown is not coming in advanced report |  |  | Screenshort | Passed - 29-3-2019 |  | Fixed (29-03-2019).
31 | TM_N_31 |  | IN grant permission why i am not able to add both users wise versa as i was able to add this before. |  |  | Screenshot | Reopen/ Pending - 1-4-2019 | can seee the same in 2.1.6.2 version issue list https://lh3.googleusercontent.com/-lF-wnQ0rsvk/W9mOYE6QWmI/AAAAAAAAEUU/xLdMLSKLCJgOOu302TaAWIUq6g8MKX15QCL0BGAYYCw/h908/2018-10-31.png | Fixed- 2-4-2019
32 | TM_N_32 |  | In grant able to add same permission multiple times |  |  | Screenshot | Reopen/ Pending - 1-4-2019 |  | Fixed- 2-4-2019
33 | TM_N_33 |  | Add sorting arrow in non-existing user table | Medium |  | Screenshot | New - 3-4-2019 |  | Fixed- 2-4-2019
34 | TM_N_34 |  | Bench mark setting page if no value is here tehn empty table boader is coming | Medium |  | Screenshot | New - 3-4-2019
35 | TM_N_35 |  | when "Importing Employee Manager" Loader runs continoulsy and page becomes unresponsive for some time.Please fix it. | High | Medium | Screenshot | Passed -21-5-2019 |  | Fixed- 21-5-2019
36 | TM_N_36 |  | Please align this icon parallel to checkbox | Low | Low | Screenshot | Passed -21-5-2019 |  | Fixed- 21-5-2019
37 | TM_N_37 |  | Why duplicate entries are appearing here.Please fix it. | Medium | Low | Screenshot | Passed -21-5-2019 |  | Fixed- 21-5-2019
38 | TM_N_38
|  |  | User Interface is getting fully messed up at "Import Employee manager" Please fix it. | Medium | Low | Screenshot | Passed -21-5-2019 |  | Fixed- 21-5-2019
39 | TM_N_39
disable adjusted overtime check box on approved sheet
40 | TM_N_40
in daily report from to selection filter should show selected date values
41 | TM_N_41
extra 2 lines are coming in DOR
42 | TM_N_42
|  |  | NAN is coming in manager portal for timeshet appoval sheets |  |  | screenshot | New - 22-5-2019
43 | TM_N_43

## Copy of 2.1.6.12
Application Name:- Timesheet application
Version Number - V 2.1.6.12 |  |  |  |  | Priority/ Severity level :- |  | Bug status:-
Date:-25-3-2019 |  |  |  |  | Critical |  | Passed
Author-Priyanka Saroch |  |  |  |  | High |  | Failed
[5 empty] | Medium |  | Reopen/ Pending
[5 empty] | Low |  | Open
New
Sr No. | Bug Id | Module Name | Description | Priority | Severity | Browser / Image links | Bug Status | QA comments | Dev Status | Release Information
4 | TM_N_04 |  | In Grant permission page on App User dropdown should be shown in alphabetical order |  |  | Screenshot | New - 25-3-2019 |  | Fixed Verified (26-04-2019)- Shadab
6 | TM_N_06 |  | Also make the navigation links in single link on different pages it's behaving in two links this should not happen | Low | Low | Screenshot | Reopen/ Pending - 29-3-2019 | IN emplloyeee account on project page its not coming correct | Fixed(29-03-2019) Verified (26-04-2019)- Shadab
10 | TM_N_10 |  | When the name or user is changed from Name + surname to surname + name then in approved reports of employs and manager the timesheet value is comiing 00 ---- seeger | High |  |  | Block- 29-3-2019 |  | Not an issue.
11 | TM_N_11 |  | When color is changed the selected font also get changed this should not happen | Medium |  |  | New - 26-3-2019 |  | Fixed Verified (26-04-2019)- Shadab
14 | TM_N_14 |  | On session expire if timeshet is tried to be submitted then its not submited and error is coming in console |  |  | Screenshot | New - 27-3-2019
22 | TM_N_22 |  | When the license is just updated and user directly goes and click on " Click here to see non-existing user's" link then for the first time its doesnot show any data . As i have imported managers in the page and again clicks the same link the data starts appearly . This should not happen. | High |  | Screenshoot | Block- 29-3-2019 |  | Data will be display after import excel. If non-existing user is present in the excel sheet.
31 | TM_N_31 |  | In grant permission why i am not able to add both users wise versa as i was able to add this before. |  |  | Screenshot | Passed - 2-4-2019 | can seee the same in 2.1.6.2 version issue list https://lh3.googleusercontent.com/-lF-wnQ0rsvk/W9mOYE6QWmI/AAAAAAAAEUU/xLdMLSKLCJgOOu302TaAWIUq6g8MKX15QCL0BGAYYCw/h908/2018-10-31.png | Fixed- 2-4-2019 Verified (26-04-2019)-Shadab
32 | TM_N_32 |  | In grant able to add same permission multiple times |  |  | Screenshot | Passed - 2-4-2019 |  | Fixed- 2-4-2019 Verified (26-04-2019)-Shadab
33 | TM_N_33 |  | Add sorting arrow in non-existing user table | Medium |  | Screenshot | New - 3-4-2019 |  | Fixed- 2-4-2019
34 | TM_N_34 |  | Bench mark setting page if no value is here then empty table boader is coming | Medium |  | Screenshot | New - 3-4-2019 |  | Fixed Verified (26-04-2019)-Shadab
35 | TM_N_35 |  | The table on Grant permisiion page is not alligned properly | High | Low | Screenshot | Passed - 2-4-2019 |  | Fixed Verified (26-04-2019)-Shadab
36 | TM_N_36 |  | the link name of "New timesheet' why its changed to "New timesheets" | High |  | Screenshot | Passed - 2-4-2019 |  | Fixed Verified (26-04-2019)-Shadab
37 | TM_N_37 |  | In PST time zone if friday is the weekending date then its taking saturday as its date automatically | Critical | Critical |  | New - 9-4-2019
38 | TM_N_38 |  | The message on Non-existing user logs when no value is present should be aligend with the above page heading | Low |  | screenshot | New - 9-4-2019 |  | Fixed Verified (26-04-2019)-Shadab
39 | TM_N_39
40 | TM_N_40
41 | TM_N_41
42 | TM_N_42
43 | TM_N_43