## Summary
Course Ahead App
| Overall progress of the QA cycle(Ontime, delayed, Stopped) | On time
| Total number of test cases | 80
| Number of testers | 1
| Test cycle duration | 12days
Status Date |  | Use Case No.
| Number of test cases planned | 80
| Number of test cases executed | 70
| Number of test cases executed overall | 70
| Number of defects encountered today | worked on fixed module
| Number of defect encountered so far | worked on fixed module
| Number of critical defects- still open | worked on fixed module
Overall status
| Number of test cases planned | 80
| Number of test cases executed | 70
| Percentageof executed testcases | 85%
| Defects density | 0
| Critical defects percentage | 0%

## Detailed status
Module | Scenarios | Sub Levels | Complexity | Responsible tester | Date of Execution(Can be past, present or future date) | Status(Pass/Fail/blocked/not executed) | Defect ID- Brief description | Severity | Status
Scoutfoto | Login Form | 1)Open URL 2)Enter User Name /Password 3)Click on login 4)Click on Logout | Complex | Priyanka | 2015-06-10 | Pass |  | High | Pass
| Login Form (Must display error message) | 1)Open URL 2)Enter User Name="Priyanka" Enter Empty Password ="" 3)Click on login 4)Click on Logout | Medium | Priyanka | 2015-06-11 | Pass |  | Medium | Pass
| Login Form + 2 (Must display error message) | 1)Open URL 2)Enter Empty User Name=" " / "s" " #$%$" Enter Password ="ardent@123" 3)Click on login 4)Click on Logout | Medium | Priyanka | 2015-06-11 | Pass |  | Medium | Pass
| Login Form + 2 (Must display error message) | 1)Open URL 2)Enter Empty User Name=" " Enter Empty Password ="" / "w" / "$#%^" 3)Click on login 4)Click on Logout | Medium | Priyanka | 2015-06-12 | Pass |  | Medium | Pass
| Login Form (Must display error message) | 1)Open URL 2)Enter Wrong User Name="wrongusnm " Enter wrong Password ="wrongpass" 3)Click on login 4)Click on Logout | Medium | Priyanka | 2015-06-12 | Pass |  | Medium | Pass
| Login Form (Forget Password link) | 1)Open URL 2)Click on Forget password link 3)New Page with UserName Text box appear | High | Priyanka | 2015-06-15 | Pass |  | High | Pass
| Login Form (Forget Password link) | 1)After the forget password page gets open 2)Enter User Name 3)Click on Submit 4)User must recive the email | High | Priyanka | 2015-06-15 | Pass |  | High | Pass
| Login Form(wrong username ) (Forget Password link) | 1)After the forget password page gets open 2)Enter "wrong "User Name 3)Click on Submit 4)User must recive the email | High | Priyanka | 2015-06-15 | Pass |  | High | Pass
Scoutfoto (Admin Page)Event creation | Event Creation (From admin paid event) | 1)Open URL 2)Enter User Name /Password 3)Click on login 5)Enter Event name 6)Enter location 7)Enter GPSlocation 8)Enter date 9)Enter map my run link 10)Check for tagging 11)Check for paid Enter paid details 12)click on save button 13)Click on Logout | High | Priyanka | 2015-06-16 | Pass |  | High | Pass
Scoutfoto (Admin Page)Event creation | Event Creation (From admin free event) | 1)Open URL 2)Enter User Name /Password 3)Click on login 5)Enter Event name 6)Enter location 7)Enter GPSlocation 8)Enter date 9)Enter map my run link 10)Check for tagging 11)Check for Free 12)click on save button 13)Click on Logout | High | Priyanka | 2015-06-16 | Pass |  | High | Pass
Scoutfoto (Admin Page)Watermark pop up. | Event Creation (From admin free event) | 1)Open URL 2)Enter User Name /Password 3)Click on login 5)Enter Event name 6)Enter location 7)Enter GPSlocation 8)Enter date 9)Enter map my run link 10)Check for tagging 11)Check for Free 12)click on save button 13)click on water mark window 14)Add values in the water mark window | High | priyanka | 2015-06-17 | Pass |  | High | Pass
Scoutfoto (Admin Page)Watermark updation in created event. | Event creation page (Watermark functionality) | 1)Login and Search event 2)open watermark window for the searched event 3)Select watermark type :- 1)Text . OR(Done for both) 2)Image 4)Enter details and Update | High | priyanka | 2015-06-18 | Pass |  | High | Pass
| Event creation page (Watermark functionality) | 1)Login and Search event 2)open watermark window for the searched event 3)Select watermark type :- 1)Text . OR(Done for both) 2)Image 4)Added the water mark image i.e(browser image water mark) 5)Enter details and Update | High | priyanka | 2015-06-19 | Pass |  | High | Pass
| Event creation page (Watermark functionality) | 1)Login and Search event 2)open watermark window for the searched event 3)Select watermark type :- 1)Text . OR(Done for both) 2)Image 4)Added the water mark image i.e(browser image water mark) 5)Enter details and Update | High | priyanka | 2015-06-22 |  |  | Medium | Pass
Scoutfoto (Admin Page)Details in created event. | Event creation page (Details functionality) | 1)Login and Search event 2)open deatils window for the searched event 3)Select emailblast file 4)Enter details and Update 5)Close the window | High | priyanka | 2015-06-25 | Pass |  | High | Pass
Image process of same created event. | Image process | 1)Open Image process page 2)Select the created event 3)Add the iamges from process section 4)submit | High | priyanka | 2015-06-25 | Pass |  | High | Pass
Login From RaceOrganizer | Login page | 1)Enter (correct) user name. 2)Enter (Correct) password on the respective fields. 3)Click Sign in/Login. | High | priyanka | 2015-06-26 | Pass |  | High | Pass
Check for new event creation (Race organizer account) | evnet creation page | 1)Open URL 2)Enter User Name /Password 3)Click on login 5)Enter Event name 6)Enter location 7)Enter GPSlocation 8)Enter date 9)Enter map my run link 10)Check for tagging 11)Check for paid Enter paid details 12)click on save button 13)Click on Logout | High | priyanka | 2015-06-26 | Pass |  | High | Pass
race organizer watermark | Watermark | 1)Login and Search event 2)open watermark window for the searched event 3)Select watermark type :- 1)Text . OR(Done for both) 2)Image 4)Enter details and Update | High | priyanka | 2015-06-26 | Pass |  | High | Pass
Race organizer Notify Runner | Notify Runner | 1)Login and Search event 2)open deatils window for the searched event 3)Select emailblast file 4)Enter details and Update 5)Close the window | High | priyanka | 2015-06-26 | Pass |  | High | Pass
| Process images | Pending- silverlight control
Photographer account | login | 1)Enter (correct) user name. 2)Enter (Correct) password on the respective fields. 3)Click Sign in/Login. |  |  | 2015-06-27
| create event | 1)Open URL 2)Enter User Name /Password 3)Click on login 5)Enter Event name 6)Enter location 7)Enter GPSlocation 8)Enter date 9)Enter map my run link 10)Check for tagging 11)Check for paid Enter paid details 12)click on save button 13)Click on Logout |  |  | 2015-06-27
| Process images | Pending- silverlight control | High | priyanka | 2015-06-29 | Pass |  | High | Pass
Agent account | login | 1)Enter (correct) user name. 2)Enter (Correct) password on the respective fields. 3)Click Sign in/Login. | High | priyanka | 2015-06-29 | Pass |  | High | Pass
| Image tagging | 1)slecet event 2)Accept slot 3)Do tagging 4)submit the slot | High | priyanka | 2015-06-29 | Pass |  | High | Pass
| logout | click on logout | High | priyanka | 2015-06-29 | Pass |  | High | Pass
Agent Account | Image tagging (auto count the images and tag the no. of photos present in the slot) | Select event slecet slots |  |  | 2015-06-30 | Pass
Front end Live site | Live site | Home Races Photographers-PhotographerFAQ, Races FAQ Upload Form Search Picture The Idea The team Contact US | High | priyanka | 2015-07-01 | Pass |  | High | Pass
| Race sign up page | Enter Details for race sign up:- 1)Full Name * 2)Race Name* 3)Race City, State * 4)E-mail * 5)Race Date * 6)Map My Run | High | priyanka | 2015-07-03 | Pass |  | High | Pass
| Rcae signup page (Reamaning fields) | Enter evnet details :- 1)Full Name * 2)Race Name* 3)Race City, State * 4)E-mail * 5)Race Date * 6)Map My Run 7)Would you like to charge? Yes No 8)Do you want us to notify your runners when their photos are live? Yes No 9)Do you want to place a sponsor logo on the photos? Yes No 10)Remark 11)Click on submit 12)click on submit | High | priyanka | 2015-07-06 | Pass |  | High | Pass
Admin section | Created event setting | P/W module | High | priyanka | 2015-07-06 | Pass

## Bug report
Defect ID | Defect Description | Steps to reproduce | Severity | State | Created by | Assigned to